## Slide 1: From AI ambition to operating reality in 100 days
100-day plan & operating model · Executive Board · Example client: Nordhafen Logistik
Notes: Open with the promise: in 100 days the board sees AI running in production under the same governance as every other service. All client names and figures in this deck are illustrative.

## Slide 2: After 100 days: proof, not a PowerPoint
3
AI use cases live in production, each with a named business owner
1
operating model agreed, staffed and running under ITIL & PMI practices
−30 %
handling time in the pilot process, measured weekly against baseline
Illustrative targets. Confirmed at Gate 1 (Day 15) once the baseline is measured.

## Slide 3: Trust comes from visibility, not from promises
01
One plan, one owner
Executive sponsor, steering committee and three stage gates (PMI). Every decision has a date and an owner.
02
Service before technology
Each AI use case becomes a managed service with an owner, service levels and a change path (ITIL).
03
Humans stay in the loop
AI proposes, people decide. Every automated decision is explainable, reviewable and reversible.
04
Measured every week
One scorecard for value, service, delivery and adoption, from Day 15 until handover.

## Slide 4: Four phases, three decision gates, one steering rhythm
01 — THE PLAN

## Slide 5: 100 days, four phases, three board decisions
Mobilise
Day 1–15
Sponsor & steering set up
Stakeholder interviews
Baseline measured
Diagnose & design
Day 16–45
Use-case portfolio ranked
Target operating model
Data & risk assessment
Pilot & prove
Day 46–80
3 pilots in production
Services onboarded (ITIL)
Weekly value tracking
Scale & hand over
Day 81–100
Roadmap for next 12 months
Team trained
Run handed to owners
Gate 1
Gate 2
Gate 3
Notes: Gates follow PMI stage-gate practice: the steering committee decides go / adjust / stop at Days 15, 45 and 80.

## Slide 6: Deliverables and decisions per phase
Phase | Key deliverables | Board decision at the gate
Mobilise · Day 1–15 | Project charter, stakeholder map, RACI, KPI baseline | Gate 1: confirm scope, targets and budget envelope
Diagnose & design · 16–45 | Ranked use-case portfolio, target operating model, risk & compliance assessment | Gate 2: select 3 pilots, approve operating model
Pilot & prove · 46–80 | 3 pilots live as managed services, change & incident paths, weekly scorecard | Gate 3: scale, adjust or stop each pilot
Scale & hand over · 81–100 | 12-month roadmap, trained owners, service levels in force | Approve roadmap and run budget

## Slide 7: Who decides, who delivers, who runs it
02 — THE OPERATING MODEL

## Slide 8: One operating model, one flow of value
GOVERN
PMI governance
Executive sponsor · AI steering committee (fortnightly) · portfolio board with stage gates
DELIVER
PMI delivery
PMO · hybrid delivery: agile sprints inside stage gates · risk & benefits registers
RUN
ITIL practices
Service desk · incident · change enablement · service level management · continual improvement
ENABLE
Platform & data
AI & data platform · security & privacy · model monitoring · vendor management
Demand → value
Notes: The chevron is the ITIL value stream: every request flows from demand to value through all four layers. Terminology follows ITIL practices; confirm naming against the ITIL (version 5) publication used by the client.

## Slide 9: Clear accountability from day one
Decision | Sponsor (CEO) | CIO | CISO / DPO | Business owner | XLRTE PMO | Service owner
Prioritise use cases | A | C | C | R | R | I
Change scope or budget | A | R | I | C | R | I
Go-live of an AI service | I | A | C | R | R | R
Change to production | I | A | C | I | C | R
Data access & privacy | I | C | A | R | C | I
Service levels & incidents | I | A | I | C | I | R
R Responsible A Accountable C Consulted I Informed

## Slide 10: How you will know it works, every week
03 — PROOF AND CONTROL

## Slide 11: The pilot pays back: handling time down 30 %
Chart: 
| Base | W1 | W2 | W3 | W4 | W5 | W6 | W7
Minutes per case | 24 | 24 | 23 | 22 | 20 | 19 | 18 | 17
Average handling time per case, pilot process (minutes)
WEEKLY SCORECARD
Value
Hours saved · cost per case
Service
SLA met · change success rate · time to restore
Delivery
Milestones on time · budget variance
Adoption
Active users · tasks handled with AI
Illustrative data.

## Slide 12: Risks managed from day one
Risk | Early signal | How we manage it
Data not fit for AI | Gaps found in data assessment | Data readiness check in Diagnose; pilots only where data passes
Low adoption | Active users flat after week 2 | Business owner per use case; training; human-in-the-loop design
Compliance (EU AI Act, GDPR) | Use case touches personal data or high-risk category | CISO/DPO accountable; risk classification before Gate 2
Vendor lock-in & cost creep | Run cost per case above plan | Open interfaces; cost per case on the weekly scorecard

## Slide 13: What we need from you in the first 10 days
01
Name the executive sponsor
CEO
Day 1
02
Confirm steering committee and fortnightly cadence
Sponsor
Day 3
03
Grant access to data, systems and process owners
CIO
Day 5
04
Nominate business owners for candidate use cases
Board
Day 7
05
Approve the pilot budget envelope
CFO
Day 10

## Slide 14: Let's make the first 100 days count
P·E · XLRTE · name@example.com